## Sheet1
PRODUCT STORE
| VERSION NO: |  |  |  | TESTED BY:ASNA ASHARAF
| VERIFIED BY: |  |  |  | DATE:30/10/24
Home page
Test Id | Test Description | Test Procedure | Test Data | Expected Output | Actual Output | Status
MODULE 1 : Home page
DE_001 | check whether the URL is working | load the URL | www.demoblaze.com/ | should open the website | website is open | pass
DE_002 | Verify SSL certificate and HTTPS | 1. Open https://www.demoblaze.com/. 2. Check the URL bar for HTTPS and SSL certificate validity. | https://www.demoblaze.com/ | Website should display as secure with HTTPS and a valid SSL certificate. | Website is displayed | pass
DE_003 | Verify page load performance | 1. Measure the load time of the home page and product pages. | https://www.demoblaze.com/ | Page should load within 2-3 seconds. | Page loaded with in seconds. | pass
DE_004 | Test compatibility across browsers | 1. Open https://www.demoblaze.com/ on Chrome, Firefox. | Browsers: Chrome v96, Firefox v94. | Website should display and function correctly on all browsers. | Website displayed correctly. | pass
DE_005 | check whether the logo is present in the page | check the logo | https://www.demoblaze.com/ | Logo should present | Logo is present | pass
DE_006 | Accessibility check. | 1. Navigate the website using only the keyboard. |  | All interactive elements should be accessible via keyboard navigation. | Accessible | pass
DE_007 | Verify the UI layout and design of the homepage | 1. Open the browser and go to the homepage of https://www.demoblaze.com/. 2. Visually inspect the page layout and alignment of elements. 3. Check if the color scheme and font sizes are consistent and readable across sections. 4. Verify that the page is free from overlapping elements or other design inconsistencies. |  | The homepage should have a clean and cohesive design with consistent alignment, color scheme, and font sizes. All elements should be readable, without any overlapping or design inconsistencies. | The color scheme and fonts are good, but the alignment of the images is not proper. | fail
MODULE 2 : Navigation and Validation
DE_008 | check the module buttons | 1)click the Home button 2)click the Contact button 3)click the About us button 4)click the Cart button 5)click the Login button 6)click the Signup button | https://www.demoblaze.com/ | should show the popup for each buttons | the popup is opened | pass
DE_009 | check the category buttons | 1)click the phones button 2)click the laptops button 3)click the monitors button | https://www.demoblaze.com/ | should show the items in the selected category | show the items in the categories | pass
DE_010 | Check error messages | 1. Enter invalid input in fields |  | Invalid Data: Empty fields, wrong username format Clear, user-friendly error messages should guide user to correct errors. | Messages are shown | pass
MODULE 3: User Authentication
DE_011 | Verify login functionality | 1. Click "Login." 2. Enter valid credentials and submit. | Username: validUser Password: validPass | User should be successfully logged in and redirected to the home page. | Successfully loged in and opens the user homepage | pass
DE_012 | Check login with invalid credentials | 1. Click "Login." 2. Enter invalid credentials and submit. | Username: invalidUser Password: wrongPass | Appropriate error message should be displayed, denying access. | Error message displayed | pass
DE_013 | Verify signup functionality | 1. Click "Sign up." 2. Enter valid credentials and submit. | Username: validUsername Password: validPassword | User should be successfully signup and the message should be shown. | Successfully signedup | pass
DE_014 | Verify logout functionality | 1. Log in to the website. 2. Click the "Logout" button. | Logged-in user | User should be logged out and redirected to the home page. | Redirected to the home page | pass
Module 4: Multimedia and popups
DE_015 | Verify "About Us" popup video functionality | 1. Navigate to the "About Us" section of the website. 2. Click on the "About Us" video icon or link to open the video popup. 3. Verify that the video popup displays correctly without any page errors. 4. Check if the video loads and starts playing automatically or on click, as intended. 5. Use video controls (e.g., play, pause, volume) to ensure they function correctly within the popup. 6. Close the popup and confirm that the page returns to the previous state without issues. | None | The "About Us" video popup should: - Display correctly without page errors. - Load and play smoothly. - Respond to all video controls (play, pause, volume). - Close properly, returning the page to its previous state. | The video popup: - Displayed as expected without errors. - Loaded and played smoothly. - Video controls worked as expected. - Closed correctly and returned to the previous page. | pass
DE_016 | Verify "Contact" form popup functionality | 1. Navigate to any page where the "Contact" popup is accessible. 2. Click on "Contact" to open the contact form popup. 3. Enter valid data in all required fields: - Contact Name - Contact Email - Message 4. Click the "Send Message" button. 5. Verify that a confirmation message appears within the popup, indicating successful submission. | None | The contact form popup should: - Open correctly upon clicking "Contact." - Display a confirmation message (e.g., "Your message has been sent") within the popup after submission. - Show an error message if any required fields are left empty, preventing submission until all fields are filled. | The form allows submission without required fields being filled, and no error message appears for empty fields. | fail
Module 5: Cart functionality
DE_017 | Verify selecting a category, choosing a product, and adding it to the cart | 1. Open the browser and go to https://www.demoblaze.com/. 2. Navigate to the Category section (e.g., "Phones", "Laptops", or "Monitors"). 3. Click on the desired category (e.g., Phones). 4. Select a product (e.g., "Samsung Galaxy S6") from the product list. 5. On the product detail page, click Add to Cart. 6. Confirm a success message appears. 7. Check that the product is listed in the cart with correct details (name, price). | https://www.demoblaze.com/prod.html?idp_=1 | The selected product should be successfully added to the cart. A confirmation message should appear, and the product should be visible in the cart with the correct details. | The product is added successfully to the cart | pass
DE_018 | Verify the categories and show the results | 1.Navigate the categories . 2.Click on each category and verify that all the results are shown. | https://www.demoblaze.com/index.html# | The selected category should be shown | The products are shown as selected category. | pass
DE_019 | Verify selecting the "Phones" category and opening a product | 1. Open https://www.demoblaze.com/. 2. Navigate to the Phones category. 3. Select a product (e.g., "Samsung Galaxy S6"). 4. Verify that the product page opens correctly, showing the product details (name, price, description). | None | The product details page should display the correct product information (name, price, description). | The product details are shown successfully | pass
DE_020 | Verify selecting the "Laptops" category and opening a product | 1. Open https://www.demoblaze.com/. 2. Navigate to the Laptops category. 3. Select a product (e.g., "MacBook Pro"). 4. Verify that the product page opens correctly, showing the product details (name, price, description). | None | The product details page should display the correct product information (name, price, description). | The product details are shown successfully | pass
DE_021 | Verify selecting the "Monitors" category and opening a product | 1. Open https://www.demoblaze.com/. 2. Navigate to the Monitors category. 3. Select a product (e.g., "Apple Monitor 24"). 4. Verify that the product page opens correctly, showing the product details (name, price, description). | None | The product details page should display the correct product information (name, price, description). | The product details are shown successfully | pass
DE_022 | Verify that the "Add to Cart" button on the product listing page adds the product to the cart and displays a confirmation message | 1. Open the browser and go to https://www.demoblaze.com/. 2. Navigate to a category (e.g., Phones). 3. Locate the "Add to Cart" button next to any product on the category page. 4. Click the Add to Cart button. 5. Confirm the success message or alert (e.g., "Product added"). 6. Navigate to the Cart page and verify that the product is listed with correct details (name, price, and quantity). | None | Each click should increment the quantity of the product in the cart. The cart should display the correct quantity and total price for the product. | The product was successfully added . | pass
DE_023 | Verify that clicking the "Add to Cart" button multiple times for the same product updates the quantity in the cart correctly | 1. Open the browser and go to https://www.demoblaze.com/. 2. Navigate to a category (e.g., Phones). 3. Select a product (e.g., "Samsung Galaxy S6"). 4. Click the Add to Cart button multiple times (e.g., 2 or 3 times). 5. Confirm each success message (e.g., "Product added"). 6. Navigate to the Cart page and verify that the product quantity reflects the number of times the button was clicked. | None | Each click should increment the quantity of the product in the cart. The cart should display the correct quantity and total price for the product. | Added products are shown in the cart | pass
DE_024 | Verify that clicking the "Add to Cart" button multiple times for the same product does not increment the quantity but creates multiple separate entries in the cart | 1. Open the browser and go to https://www.demoblaze.com/. 2. Navigate to a category (e.g., Phones). 3. Select a product (e.g., "Samsung Galaxy S6"). 4. Click the Add to Cart button multiple times (e.g., 2 or 3 times). 5. Confirm each success message (e.g., "Product added"). 6. Navigate to the Cart page and observe how the product is displayed. | None | Clicking the "Add to Cart" button multiple times for the same product should increment the quantity of the product in the cart (e.g., quantity = 3 after 3 clicks). The total price should update based on the quantity. | Adding the same product multiple times creates separate entries in the cart instead of incrementing the quantity. | fail
DE_025 | Verify that products from different categories can be added to the cart simultaneously | 1. Select a product from Phones and add it to the cart. 2. Select a product from Laptops and add it to the cart. 3. Navigate to the Cart page and verify that all products are listed correctly. | Products: Phone (Samsung Galaxy S6), Laptop (Sony Vaio) | All selected products should be displayed in the cart with accurate details. | Selected products are displayed in the cart. | pass
DE_026 | Verify that the cart retains the added products after refreshing the page | 1. Add a product to the cart. 2. Refresh the page. 3. Navigate to the Cart page and confirm that the product is still present. | None | The product should remain in the cart after the page refresh. | The product is diplayed in the cart after page refresh. | pass
DE_027 | Verify that if the same product is added multiple times, the cart updates the quantity and reflects the total price in a single entry instead of creating separate entries. | 1. Open the browser and navigate to https://www.demoblaze.com/. 2. Select a product (e.g., "Samsung Galaxy S6"). 3. Click the Add to Cart button once and verify that the product is added to the cart. 4. Click the Add to Cart button for the same product again. 5. Navigate to the Cart page and verify the product details. | None | The cart should show the product as a single entry. The quantity should increment. The price should update accordingly. | The cart shows the product as separate entries and the price is also shown as separate instead of total price of the same quantity | fail
DE_028 | Verify that adding the same product multiple times updates the quantity in a single entry instead of creating separate entries. | 1. Open the browser and go to https://www.demoblaze.com/. 2. Navigate to a category (e.g., Phones). 3. Select a product (e.g., "Samsung Galaxy S6"). 4. Click the Add to Cart button multiple times (e.g., 3 times). 5. Navigate to the Cart page and observe how the product is displayed. | None | The cart should show the product as a single entry, with the quantity updated. The total price should also update accordingly. | The cart shows the product as separate entries for each addition instead of updating the quantity. | fail
DE_029 | Verify that a product can be successfully deleted from the cart. | 1. Open the browser and navigate to https://www.demoblaze.com/. 2. Add a product to the cart (e.g., "Samsung Galaxy S6"). 3. Navigate to the Cart page. 4. Click the Delete button next to the product in the cart. 5. Verify that the product is removed from the cart and the total price is updated. | None | The product should be successfully removed from the cart. The cart should reflect the updated total price (excluding the deleted product). | The product is removed from the cart after deletion and the total price is excluded. | pass
DE_030 | Verify that an appropriate message (e.g., "Your cart is empty") is displayed when the cart becomes empty after deleting all products. | 1. Open the browser and navigate to https://www.demoblaze.com/. 2. Add multiple products to the cart (e.g., "Samsung Galaxy S6" and "Sony Vaio i5"). 3. Navigate to the Cart page. 4. Delete all products from the cart one by one. 5. Observe whether an empty cart message is displayed after all products are removed. | None | After deleting all products, a message such as "Your cart is empty" should be displayed. | No message is displayed after deleting all products, leaving the cart visually empty but without confirmation of its state. | fail
DE_031 | Verify that the product remains deleted from the cart even after refreshing the page. | 1. Add a product to the cart. 2. Navigate to the Cart page. 3. Delete the product from the cart. 4. Refresh the page. 5. Verify that the deleted product does not reappear in the cart. | None | After deleting a product, it should not reappear in the cart when the page is refreshed. | After refreshing the page deleted product does not appered in the cart list. | pass
DE_032 | Verify that the user can undo a product deletion if the functionality. | 1. Add a product to the cart. 2. Navigate to the Cart page. 3. Delete the product. 4. Verify the "Undo" option is present. | None | After deletion of the product an undo option should present | There is no undo option for the user to cancel the deletion operation of the added product | fail
DE_033 | Verify that a logged-in user can add a product to the cart successfully. | 1. Navigate to the Login page. 2. Enter valid credentials and log in. 3. Browse through the product categories and select a product. 4. Click the Add to Cart button for the selected product. 5. Navigate to the Cart page to verify the product is added. | Username and password | The selected product should be added to the cart, and the cart should display the product details, including name, price, and quantity. | Successfully logged in and opens the user homepage and product was added to the cart | pass
MODULE 6: Username and Password Handling
DE_034 | Verify that the username field enforces the configured maximum character limit. | 1. Navigate to the Login page. 2. Enter a username with more than the maximum allowed characters (e.g., 51 characters for a 50-character limit). 3. Observe whether the username field prevents further input beyond the limit. 4. Submit the form and verify that no error occurs for entering within the valid limit. |  | The username field should restrict input to the maximum allowed characters (e.g., 50 characters). Any extra characters should not be accepted. | The usrname field accepts all the characters without limit | fail
DE_035 | Verify that the password is masked by default when entered in the password field. | 1. Navigate to the Login page. 2. Enter a password in the password field. 3. Observe whether the password is masked. |  | The password should appear as masked characters (••••••••) by default. | The password appear as masked | pass
DE_036 | Verify that the appropriate error message is displayed when the password entered is too short. | 1. Navigate to the Login page. 2. Enter a password shorter than the minimum required length (e.g., 5 characters for an 8-character minimum). 3. Submit the form and observe the error message. |  | The error message should appear (e.g., "Password must be at least 8 characters long"). | There is no limit for password | fail
DE_037 | Verify that the password can be copied and pasted into the password field. | 1. Navigate to the Login page. 2. Copy a valid password string. 3. Paste it into the password field. 4. Submit the form and observe the behavior. |  | The copied password should be accepted, and the form should submit successfully. | The copied password are not accepted | fail
DE_038 | Verify that the "Show Password" toggle is not available on the login page. | 1. Navigate to the Login page. 2. Observe the password field and check for the presence of a "Show Password" toggle (e.g., an eye icon or checkbox). 3. Try interacting with any control that appears to toggle password visibility. |  | The "Show Password" toggle should not be present or functional in the login form. | there is no toggle present | pass
MODULE 7: Place Order
DE_039 | Verify that the user can successfully place an order and receive confirmation. | 1. Open the browser and navigate to https://www.demoblaze.com/. 2. Add one or more products to the cart (e.g., "Samsung Galaxy S6"). 3. Navigate to the Cart page. 4. Click the Place Order button. 5. Fill in the required fields in the order form: - Name - Country - City - Credit Card - Month - Year 6. Click the Purchase button. 7. Verify that an order confirmation message or popup is displayed with details such as the order ID and total amount. |  | The order should be successfully placed, and a confirmation message should appear displaying the order ID and total amount. The cart should be cleared after the order is placed. | The order can be placed successfully | pass
DE_040 | Verify that the billing details form is visible and requires data input before proceeding. | 1. Navigate to the checkout page. 2. Verify that the Billing Details section is visible. 3. Verify that the required fields (address ,email etc) are present and must be filled. |  | The form should display all required fields, and the user should be prompted to fill them before proceeding. | There is no filed for the email and address | fail
DE_041 | Verify that the user can successfully submit the billing details form | 1. Navigate to the Billing Details form. 2. Fill out the required fields with valid data. 3. Click on the Purchase button. |  | The form should be successfully submitted, and the user should get a confirmation | Confirmation message is given | pass
DE_042 | Verify that appropriate error messages are displayed when invalid bank details are entered. | 1. Navigate to the "Place Order" form. 2. Enter invalid card details in the payment section 3. Submit the form and observe the error messages. |  | Clear, user-friendly error messages should be displayed, highlighting the invalid fields. | No error messages are given when card number entered incorrectly | fail
DE_043 | Verify that sensitive information (e.g., card number) is masked when entered. | 1. Navigate to the "Place Order" form. 2. Begin typing the CARD number in the field. 3. Observe whether the field masks the input partially. |  | The card number field should partially mask the input (e.g., displaying only the last 4 digits). | there is no masking | fail
DE_044 | Verify that no tracking or confirmation mail is sent to the user after placing an order. | 1. Navigate to the "Place Order" page. 2. Complete the purchase by filling in all required details. 3. Place the order and wait for confirmation on the website. 4. Check the registered email inbox for tracking or confirmation emails. |  | Tracking or confirmation email should be received in the registered email inbox. | no email or traking message is received | fail

## Sheet2
PRODUCT STORE
OS:WINDOWS,BROWSER TESTED BY:ASNA ASHARAF
VERIFIED BY: DATE:18/11/24
Bug Id | Test id | Bug Description | Step to reproduce | Screenshot | Severity | Priority | Expected Result | Status
BUG_001 | DE_007 | The alignment of the images on the homepage is not proper, causing design inconsistencies. | 1. Open the browser and navigate to https://www.demoblaze.com/. 2. Visually inspect the alignment of images on the homepage. 3. Observe the misalignment of images in the UI layout. |  | Minor | Medium | The homepage should have a clean and cohesive design with proper image alignment. | NEW
BUG_002 | DE_016 | The contact form allows submission without filling the required fields, and no error message appears for empty fields. | 1. Navigate to any page where the "Contact" popup is accessible. 2. Click on "Contact" to open the contact form popup. 3. Leave one or more required fields empty (e.g., Contact Name, Contact Email, or Message). 4. Click the "Send Message" button. |  | Major | High | The form should prevent submission until all required fields are filled, and display appropriate error messages for empty fields. | NEW
BUG_003 | DE_024 | Clicking the "Add to Cart" button multiple times for the same product creates separate entries in the cart instead of incrementing the quantity. | 1. Open the browser and go to https://www.demoblaze.com/. 2. Navigate to a category (e.g., Phones). 3. Select a product (e.g., "Samsung Galaxy S6"). 4. Click the "Add to Cart" button multiple times (e.g., 2 or 3 times). 5. Confirm each success message (e.g., "Product added"). 6. Navigate to the Cart page and observe how the product is displayed. |  | Major | High | Clicking the "Add to Cart" button multiple times for the same product should increment the quantity of the product in the cart. The total price should update accordingly based on the quantity. | NEW
BUG_004 | DE_027 | When the same product is added multiple times, the cart creates separate entries for each addition instead of updating the quantity in a single entry and reflecting the total price. | 1. Open the browser and navigate to https://www.demoblaze.com/. 2. Select a product (e.g., "Samsung Galaxy S6"). 3. Click the "Add to Cart" button once and verify the product is added to the cart. 4. Click the "Add to Cart" button for the same product again. 5. Navigate to the Cart page and verify the product details. |  | Major | High | The cart should show the product as a single entry. The quantity should increment with each addition, and the total price should update accordingly. | NEW
BUG_OO5 | DE_028 | When the same product is added multiple times, the cart creates separate entries for each addition instead of updating the quantity in a single entry. The total price does not update accordingly. | 1. Open the browser and go to https://www.demoblaze.com/. 2. Navigate to a category (e.g., Phones). 3. Select a product (e.g., "Samsung Galaxy S6"). 4. Click the "Add to Cart" button multiple times (e.g., 3 times). 5. Navigate to the Cart page and observe how the product is displayed. |  | Major | High | The cart should show the product as a single entry, with the quantity updated. The total price should also update accordingly. | NEW
BUG_006 | DE_030 | After deleting all products from the cart, no message such as "Your cart is empty" is displayed, leaving the cart visually empty but without confirmation of its state. | 1. Open the browser and navigate to https://www.demoblaze.com/. 2. Add multiple products to the cart (e.g., "Samsung Galaxy S6" and "Sony Vaio i5"). 3. Navigate to the Cart page. 4. Delete all products from the cart one by one. 5. Observe whether an empty cart message is displayed after all products are removed. |  | Medium | High | After deleting all products, a message such as "Your cart is empty" should be displayed to inform the user. | NEW
BUG_007 | DE_032 | After deleting a product from the cart, there is no "Undo" option available to cancel the deletion operation and restore the product. | 1. Add a product to the cart. 2. Navigate to the Cart page. 3. Delete the product. 4. Verify if the "Undo" option is present. |  | Medium | High | After deleting a product, an "Undo" option should be available to allow the user to cancel the deletion and restore the product. | NEW
BUG_008 | DE_034 | The username field does not enforce the configured maximum character limit. It accepts input beyond the set character limit. | 1. Navigate to the Login page. 2. Enter a username with more than the maximum allowed characters (e.g., 51 characters for a 50-character limit). 3. Observe whether the username field prevents further input beyond the limit. 4. Submit the form and verify that no error occurs for entering within the valid limit. |  | Major | High | The username field should restrict input to the maximum allowed characters (e.g., 50 characters). Any extra characters should not be accepted. | NEW
BUG_009 | DE_036 | There is no password length validation in place. The password field does not enforce a minimum character requirement or display an error message for short passwords. | 1. Navigate to the Login page. 2. Enter a password shorter than the minimum required length (e.g., 5 characters for an 8-character minimum). 3. Submit the form and observe the error message. |  | Major | High | The error message should appear (e.g., "Password must be at least 8 characters long") when the password entered is too short. | NEW
BUG_010 | DE_037 | The password field does not accept copied passwords. When attempting to paste a valid password, the field does not accept the input, preventing the form submission | 1. Navigate to the Login page. 2. Copy a valid password string. 3. Paste it into the password field. 4. Submit the form and observe the behavior. |  | Major | High | The copied password should be accepted, and the form should submit successfully. | NEW
BUG_011 | DE_040 | The billing details form is missing required fields, such as email and address. The user is not prompted to provide these details before proceeding with the checkout. | 1. Navigate to the checkout page. 2. Verify that the Billing Details section is visible. 3. Verify that the required fields (address, email, etc.) are present and must be filled. |  | Major | High | The form should display all required fields (address, email, etc.), and the user should be prompted to fill them before proceeding. | NEW
BUG_012 | DE_042 | The payment form does not display any error messages when invalid card details, such as an incorrect card number, are entered. | 1. Navigate to the "Place Order" form. 2. Enter invalid card details in the payment section. 3. Submit the form and observe the error messages. |  | Major | High | Clear, user-friendly error messages should be displayed, highlighting the invalid fields, such as incorrect card number. | NEW
BUG_013 | DE_043 | The card number field does not mask sensitive information when entered. There is no partial masking of the card number (e.g., displaying only the last 4 digits). | 1. Navigate to the "Place Order" form. 2. Begin typing the card number in the field. 3. Observe whether the field masks the input partially. |  | Major | High | The card number field should partially mask the input, displaying only the last 4 digits for security purposes. | NEW
BUG_014 | DE_044 | No tracking or confirmation email is sent to the user after placing an order. The user does not receive any email confirming the order or providing tracking details. | 1. Navigate to the "Place Order" page. 2. Complete the purchase by filling in all required details. 3. Place the order and wait for confirmation on the website. 4. Check the registered email inbox for tracking or confirmation emails. |  | Major | High | A tracking or confirmation email should be sent to the registered email inbox after placing the order. | NEW